## Slide 1
PI submits project proposal to NURail
Project proposal sent to TAC for review
Occurs at least 90 days prior to start of project
Sent to TAC no later than 15 days after receiving from PI
TAC completes review and project added to active list
TAC review done within 30 days
PI completes project description form and submits to NURail
PI completes project description form within 15 days after request for document
Project description added to RiP database and posted on NURail website
PI updates project description/provides status report coincident with NURail semi-annul reporting
RPC completes within 15 days after form completed by PI
Due within 15 days of request from RPC, done on a semi-annual basis, and continued until project completion
Will project be completed by proposed or revised end date?
No
Yes
PI submits draft of the final report to NURail for review
RPC sends reminders to PI about due date for final report
PI sends request for extension to NURail within 15 days of original end date.
Will project be extended to another NURail grant?
PI submits interim report to NURail
Yes
No
Revisions requested by NURail?
Yes
No
Final report posted to NURail website and report distributed to TRB and other US DOT repositories
Process begins with PI’s project concept
PI makes revisions to draft of the final report
Projects extended from one grant to another are required to submit an interim report by the end of first grant
PI submits draft within 60 days after project end date
NURail reviews will be completed within 15 days after receipt of draft
PI will complete edits within 30 days after receiving revision request
RPC responsible for posting and distributing report